## Sheet1
Task Name | Start Date | End Date | Duration
Workshop 1: Project kick off | 2024-05-13 | 2024-05-19 | 6
Project Start /Supervisor assignment | 2024-05-20 | 2024-05-26 | 6
Searching topics | 2024-05-27 | 2024-06-02 | 6
Creating Proposal | 2024-05-27 | 2024-06-02 | 6
Proposal Submission | 2024-06-03 | 2024-06-09 | 6
PPT Presentation for problem | 2024-06-10 | 2024-06-23 | 13
Creating Trello, Github and Gantt Chart | 2024-06-17 | 2024-07-09 | 22
workshop 2: Literature review and critical thinking | 2024-07-10 | 2024-07-10 | 0
Data Preprocessing | 2024-07-11 | 2024-07-17 | 6
Mid-point Review submission | 2024-07-22 | 2024-07-22 | 0
Model development | 2024-07-23 | 2024-07-28 | 5
Model Training | 2024-07-29 | 2024-08-02 | 4
Model Evaluation | 2024-08-03 | 2024-08-06 | 3
Fine tune the model | 2024-08-07 | 2024-08-14 | 7
Model Testing | 2024-08-15 | 2024-08-22 | 7
Documentating the Reports | 2024-07-23 | 2024-08-25 | 33
Project Submission | 2024-08-26 | 2024-08-27 | 1